PROJECT PLANNING PHASE
PocketSmart AI – Project Planning Template

| Date | 30 September 2026 |
| --- | --- |
| Team ID |  |
| Project Name | PocketSmart AI: Your Smart Budget & Recommendation Analysis |
| Maximum Marks | 8 Marks |

Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup | USN-1 | As a developer, I can initialize the PocketSmart AI project structure and environment. | 2 | High |  |
| Sprint-1 | Authentication | USN-2 | As a user, I can register and securely log into PocketSmart AI. | 3 | High |  |
| Sprint-1 | User Profile | USN-3 | As a user, I can save my preferences and savings goal. | 2 | Medium |  |
| Sprint-1 | Transaction Management | USN-4 | As a user, I can add, edit and delete income and expense transactions. | 5 | High |  |
| Sprint-1 | Database | USN-5 | As a developer, I can persist users, transactions and profile data reliably. | 3 | High |  |
| Sprint-2 | Budget Planning | USN-6 | As a user, I can create and manage a monthly/category budget. | 3 | High |  |
| Sprint-2 | Dashboard | USN-7 | As a user, I can view income, expenses, balance and budget status. | 5 | High |  |
| Sprint-2 | Spending Analytics | USN-8 | As a user, I can see category-wise spending and spending trends. | 3 | High |  |
| Sprint-2 | AI Recommendations | USN-9 | As a user, I can receive personalized recommendations based on my spending. | 5 | High |  |
| Sprint-2 | Alerts & History | USN-10 | As a user, I can view transaction history and receive budget-limit alerts. | 2 | Medium |  |
| Sprint-3 | Integration | USN-11 | As a user, I can use all PocketSmart AI features through one integrated application. | 3 | High |  |
| Sprint-3 | Recommendation UI | USN-12 | As a user, I can read AI recommendations and their supporting insights clearly. | 3 | High |  |
| Sprint-3 | Validation & Errors | USN-13 | As a user, I receive clear feedback for invalid input or failed requests. | 2 | Medium |  |
| Sprint-3 | Testing | USN-14 | As a project team, we can verify the system through functional and integration tests. | 5 | High |  |
| Sprint-3 | Documentation & Demo | USN-15 | As a project team, we can present the completed PocketSmart AI system with documentation. | 3 | High |  |

Sprint Schedule & Project Tracker

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 15 | 6 Days | 01 Oct 2026 | 06 Oct 2026 | 15 | 06 Oct 2026 |
| Sprint-2 | 18 | 6 Days | 07 Oct 2026 | 12 Oct 2026 |  |  |
| Sprint-3 | 16 | 6 Days | 13 Oct 2026 | 18 Oct 2026 |  |  |

Velocity

Planned total story points = 15 + 18 + 16 = 49.
Planned number of sprints = 3.
Average planned velocity = 49 / 3 = 16.33 story points per sprint.

Actual velocity should be updated using completed story points after each sprint. This prevents the planning document from treating estimated work as completed work.

Burndown Chart

A burndown chart should track remaining PocketSmart AI story points against the remaining sprint days. At the start of each sprint, enter the total committed points. Each day, subtract completed story points and record the remaining work. The chart can be maintained in Excel/Google Sheets and inserted into the final documentation.

Suggested tracking columns: Sprint Day | Planned Remaining Points | Actual Remaining Points | Completed Points | Notes.

Planning Notes

Story points are estimates of relative effort, not hours.

High-priority stories should support the minimum usable PocketSmart AI product first.

AI recommendation quality should be tested using representative spending scenarios before final demonstration.

Security and privacy checks are required because the application processes personal financial information.

Dates can be changed to match the team's actual academic project schedule.